## Homepage
Menu Name/File Name | Element | Result | Should Be | Remarks | Status
Home > Register | Submit Button | No Response | Save as new volunteer record
About US > Gospel Conversation/Exposed/Prayed to Receive/Followup | Numbers |  | Display the actual count of Contact with these Status :Total, regardless of region
Upcoming Events | Left Side: Calendar |  | Display all Upcoming Events
Upcoming Events | Right Side |  | Display all Upcoming Events with Photos
Accomplishments | Gallery of Activities |  | Display Most Recent Activities
Organizations | Gallery of Small Groups |  | Change Menu Name to Small Groups Display details about small Groups: Group Name, Leader name, Contact Info of Leader

## Member
Menu Name | Element | Result | Should Be | Remarks | Status
Calendar | Click Event | Events are displayed in localhost but not in server | Display Event Details once clicked Event Name, Date From and To, Location , Event Description, Category Leader
Joined Event List | Click Event | Display Event Details: Event Name, Date From and To, Leader | Display Event Details: Tab 1: Event Name, Date From and To, Location , Event Description, Category Leader Tab 2: Activities Tab 3: Logistics, Remove Register button Add Withdraw Registration
Joined Event List > Click Event > Register | Confirmation Modal | "You will be joining this event: 2" | Display the event name not the ID
Joined Event List > Click Event > Contacts | Add | N/A | Members/Volunteers should be able to add new Contacts who came in the event (Guest Name, Contact No, Address, Description) This is linked with the Event Management > Attendance in Group Leader module | Also Applicable to Group Leaders
Joined Events List >Click Event >Contacts | Update | N/A | Members/Volunteers should be able to update the Contact No, Address, Description and Status of Contacts (Gospel conversation, Exposed, Prayed to Receive, Followed Up) This is linked with the Event Management > Attendance in Group Leader module
Joined Events List >Click Event >Contacts | Send SMS | N/A | Member/Volunteers should be able to send Templated Follow up SMS to the new Contacts
Incoming Events | Click Event | Display Event Details once clicked | Include Event Name, Date From and To, Location , Event Description, Category Leader Do not display Register button if member is already registered to that event
Joined Group List | Click Group name | no action | Display Group Details: Group Name, Description, Leader
Suggested Groups | Click Group name | no action | Display Group Details: Group Name, Description, Leader Do not include the joined group in the list
Suggested Materials List | Click Material Name | N/A | Display details of Materials added by the groupleader: Name, Description *depending on the events

## Group Leader
Menu Name | Element | Result | Should Be | Remarks | Status
Dashboard - Gospel Conversation, Exposed, Prayed To Receive, Followup | Text | Not yet the actual count | Display the number of Contacts with these status
Dashboard - Key Contacts | Graph | Not yet the actual count | *could be merged into one graph, use legends
Dashboard -Members | Graph | Not yet the actual count
Dashboard -Groups | Graph | Not yet the actual count
Dashboard -Events | Graph | Not yet the actual count
Dashboard - Ethnics per Region | Graph | Displays only one detail on drill down
Dashboard - Religion per Region | Graph | Displays only one detail on drill down
Dashboard - Language per Region | Graph | Displays only one detail on drill down
Dashboard - Religions in Mindanao | Graph | Displays only one detail on drill down
Event Management>Add Event | City |  | Display details about the selected location text mined Language, Ethnic Groups, Religion
Event Management>Add Event | Event Date |  | Display weather forecast on the selected date
Event Management>Add Event | Events List | Displays the Event ID | Hide the event ID
Event Management>Add Event>Events List | Edit button | Modal do not appear | Should be able to edit the event details
Event Management>Add Event>Events List | Delete button | Modal do not appear | Should be able to delete the upcoming events with no connected Logistics, Materials, Activities
Event Management> Activities | Add | Adds new row | Rename to "Add Row"
Event Management> Activities | Add | Saves the Activities to database | Rename to "Save"
Event Management>Activities>Events List | View button | Modal displays list of activities under the selected event Button name do not appear | Display the button name | *Same observations in Logistics, Attendance, Groups, Group Members and Materials
Event Management>Activities>Events List | red button | Modal do not appear Button name do not appear | Display the button name
Event Management>Activities>Events List |  | Displays the Event ID | Hide the event ID
Materias > Add Material | Add Button | Accepts Blank entries | Material Name should be required

## Admin
Menu Name | Element | Result | Should Be
Dashboard - Gospel Conversation, Exposed, Prayed To Receive, Followup | Text | Not yet the actual count | Display the number of Contacts with these status
Dashboard - Key Contacts | Graph | Not yet the actual count | *could be merged into one graph, use legends
Dashboard -Members | Graph | Not yet the actual count
Dashboard -Groups | Graph | Not yet the actual count
Dashboard -Events | Graph | Not yet the actual count
Dashboard - Ethnics per Region | Graph | Displays only one detail on drill down
Dashboard - Religion per Region | Graph | Displays only one detail on drill down
Dashboard - Language per Region | Graph | Displays only one detail on drill down
Dashboard - Religions in Mindanao | Graph | Displays only one detail on drill down
CRUD Modules | Lists | Displays the ID | Hide the ID
| Edit/View button | Modal do not appear | Should be able to edit the details | Only User Management Module shows button name "E and D"
| Delete button | Modal do not appear | Should be able to delete the records with no connection to other modules
User Management>Add User | Place holders | uses "Enter your PAssword" as placeholder
| Add Button | uses "Sign In" as button name
Logo |  |  | Use YAVATAN Logo